Organising a Conference

RDGC/Humanities Postgraduate Research and Professional Skills Training

Dr Lisa Bernasek, l.bernasek@soton.ac.uk

The main questions:

- Content: What is the conference about? What format will it have?

- Finance: What will the costs be and how will they be covered?

- Marketing: How will you get people to attend?

- Administration: Who will do all the work?

Timeline

12-18 months before:

- decide theme, format and possible keynote speakers;

- think about costs and budget;

- decide venue, date

9-12 months before:

- invite keynote speakers;

- set up conference website;

- issue Call for Papers;

- put together costs and budget;

- apply for funding or identify sponsors;

- decide conference fee

6-9 months before:

- deadline for Call for Papers;

- accept/reject papers, decide panels and confirm with speakers

4-6 months before:

- advertise conference and open registrations;

- collect information from delegates on special requirements related to disability or diet

1-2 months before:

- continue publicising and taking registrations;

- book travel or hotel for invited speakers;

- provide final numbers to venue;

- allocate panel chairs

Final issues (1-2 weeks before):

- printing programme, name badges, preparing delegate packs;

- posting materials to venue if necessary;

- assigning jobs on the day

Your conference date!

- Register attendees

- Check A/V working

- Reconfirm catering arrangements

- Keep to time

- Evaluation forms

Group exercise: In a group of 4-5 you will discuss and decide how to organise your own conference. You will need to decide…

Content

- A theme for your conference

- A format and rough timetable (number of days, sessions, etc.)

- Possible keynote speakers

- How many delegates you would like to attract

Funding:

- Costs that will need to be paid out for your conference

- Work or costs that will be donated

- Possible sources of funding or sponsorship

- Will you need to charge a fee?

Marketing

- Which disciplines your conference might attract and how to publicise to them

- How you might reach different audiences: Postgraduate students, interdisciplinary researchers, outside academia….

- Identify email lists or websites you might target to list the conference

- Do you want a printed poster or postcard?

Administration

- List the jobs that will need to be done in the 2 weeks before the conference

- List the jobs that will need to be done on the day of the conference

- How many people will you need on the day of the conference to help?